Risk Reflection Statements

1. You know it’s not really a risk when…

- Treat events that have already occurred as issues, not risks.

- Avoid vague or generic risk descriptions; be specific.

- Ensure the risk has a clear impact and uncertainty.

- Exclude routine activities from the risk register.

- Validate that entries are genuine risks, not assumptions or concerns.

2. A real risk always includes…

- Include a clearly defined cause and impact in every risk description.

- Ensure the risk includes a specific event that may occur.

- Assess and document the probability of the risk occurring.

- Assign a responsible owner for each risk.

- Link the risk to project objectives such as cost, schedule, or quality.

- Perform qualitative or quantitative assessment of the risk.

3. If a register entry doesn’t have a clear trigger, Its probably....

- Avoid vague or ambiguous entries, risks should be clearly defined with a specific cause, event, and impact.

- Distinguish risks from uncertainties and assumptions.

- Ensure risks are linked to project objectives.

- Challenge entries that resemble business-as-usual.

- Require a basis of estimate for probability and impact.

4. You can spot a weak mitigation by looking for….

- Avoid vague or generic language, Terms like “monitor”, “discuss”, or “raise awareness”.

- Ensure each mitigation has a clear owner.

- Include specific actions with measurable outcomes and deadlines.

- Avoid repetition across multiple risks without tailoring.

- Link mitigation actions to project schedule, cost, or deliverables.

- Challenge business-as-usual activities listed as mitigations.

- Verify that mitigations are proactive, not passive.

- Ensure regular review and updates.

5. The most credible mitigations I’ve seen always…

- Assign a clear owner to each mitigation action.

- Ensure all mitigations are time-bound with deadlines.

- Include budget estimates for mitigation actions.

- Link mitigation actions to the project schedule.

- Design mitigations to meet SMART criteria.

- Define measurable outcomes for each mitigation.

- Use proactive actions that reduce risk probability or impact.

- Avoid vague or generic mitigations like 'monitor' or 'raise awareness'.

6. Residual (post-mitigated) risk score should drop when...

- Reassess risk only after mitigation actions have been completed or show measurable progress.

- Ensure mitigation actions are tracked and reviewed regularly to validate effectiveness.

- Update residual risk scores only when there is clear evidence of reduced probability or impact.

- Maintain audit trails or documentation to support changes in risk scoring.

- Avoid arbitrary score reductions without supporting data or completed actions.

- Use SMART criteria to evaluate whether mitigations justify a lower residual score.

7. I get suspicious of a mitigation plan when…

- Avoid vague or generic mitigation plans. Lack of ownership, deadlines, or specificity is a red flag.

- Be cautious of overly optimistic mitigation plans.

- Ensure mitigation plans are aligned with the specific risk cause and impact.

- Challenge mitigation plans that do not reduce the risk exposure over time.

- Avoid reusing the same mitigation across multiple risks without tailoring.

8. A mitigation without a time frame is…

- Ensure all mitigations include a clear timeframe.

- Avoid vague or generic mitigation descriptions. Mitigations should be specific and meaningful, not broad or ambiguous.

- Assign ownership and accountability for each mitigation.

- Track and monitor mitigation progress against deadlines.

- Elevate the priority of time-sensitive mitigations.

- Integrate mitigation timelines into project planning.

9. Strong mitigations don’t just say ‘monitor’ — they…

- Include specific actions.

- Assign clear ownership.

- Make them time-bound.

- Define measurable outcomes.

- Ensure they are proactive.

10. If the same mitigation appears on multiple risks, I.......

- Review risks with identical mitigations to ensure they are not duplicates.

- Challenge copy-paste mitigations and tailor actions to each specific risk.

- Group risks with a common cause and develop a shared mitigation plan.

- Avoid generic mitigations; ensure each action is specific and relevant.

- Assess whether shared mitigations are efficient and cost-effective.

- Re-evaluate risks where mitigations appear ineffective or unchanged.

Scenario Prompts

1. "Scenario 1:  The risk register shows a high-scoring risk related to late subsystem integration. A mitigation plan exists: “Weekly interface calls to resolve issues.” The risk remains open with a high post-mitigated exposure for 3 months with no change. What do you notice?  What would you challenge? What would you expect to see in a stronger mitigation?"

- Challenge vague mitigations like 'weekly calls' that do not specify actions, owners, or outcomes.

- Replace business-as-usual activities with targeted, time-bound mitigation steps.

- Review the effectiveness of existing mitigation actions and assess why the risk score remains high.

- Ensure mitigation actions are SMART.

- Escalate unresolved risks to senior stakeholders if no progress is made over time.

- Break down the risk into smaller components and address root causes individually.

- Track and document progress of mitigation actions to justify changes in residual risk exposure.

- Update the risk register regularly to reflect mitigation status and impact.

2. "Scenario 2:  A supply risk has 5 mitigation actions listed. They are: ‘raise awareness’, ‘build stakeholder support’, ‘hold monthly review’, ‘track lead times’, ‘use buffer inventory’. Risk remains amber. How would you assess this mitigation set? Which of these (if any) would you question? What evidence would you ask for?"

- Avoid vague or generic mitigation actions. Terms like “raise awareness” or “build stakeholder support” must specify who, how, and what outcome is expected.

- Challenge business-as-usual activities.

- Ensure each mitigation is SMART.

- Request evidence of mitigation effectiveness.

- Clarify buffer inventory usage.

- Assess root cause coverage.

- Encourage revision of vague mitigations.

3. "Scenario 3:	A cost risk has now occurred. Two of its mitigations are still open: “Review contract terms” and “Engage finance partner”. No update to register status. What does this tell you about the quality of mitigation monitoring? What would you advise the PMO to do? Is this a process or behaviour issue?"

- Close the risk and reclassify it as an issue.

- Review and update the risk register immediately.

- Assess whether the mitigation actions were ever implemented.

- Assign clear ownership and due dates to all mitigation actions.

- Engage relevant stakeholders in an urgent review meeting.

- Evaluate the effectiveness and relevance of existing mitigations.

- Increase the frequency and rigour of risk reviews.

- Provide training to improve risk management behaviours.

- Use lessons learned to improve future mitigation planning.

4. "Scenario 4:   A register entry states: “There is a concern that the design may not meet stakeholder expectations.” No trigger, no probability, no mitigation. Owner says they’re ‘keeping it under review’. Is this a risk, an uncertainty, or a worry? Why? What would you expect to see if it were a genuine risk? What action would you take if this were your register?"

- Reject vague entries that lack a defined cause, event, and impact.

- Clarify whether the concern is a risk, issue, or uncertainty.

- Request the risk owner to specify which design elements and stakeholder expectations are at risk.

- Ensure the entry includes a trigger, probability, and mitigation plan.

- If no mitigation is possible, consider retiring the entry or reclassifying it as a worry.

- Engage stakeholders to validate expectations and assess alignment with design requirements.

- Use structured risk formats.

5."Scenario 5:  Three different risks in the register list the exact same mitigation: “Engage stakeholder group and increase awareness.” Residual risk scores have not changed. What concerns you about this? Is this a sign of weak mitigation or acceptable practice? What would you do differently in risk review?"

- Review whether the risks are duplicates or share a common cause.

- Avoid copy-paste mitigations.

- Ensure stakeholder engagement details are specific and measurable.

- Challenge vague mitigations like “increase awareness”.

- Reassess mitigation effectiveness if residual scores remain unchanged.

- Use risk reviews to validate shared mitigations.

- Encourage SMART mitigation actions.

- Escalate weak or generic mitigations.