## Work To Do List
Important / Urgent | Important / Not-Urgent
Technical: 1) Clean up the data files for LLM 2) Set up LLM 3) Confirm LLM token issue with organisers 4) Connect LLM to UI to allow for transmission and receiving of data by/to user | Technical: 1) Include schedule impact
UI / Float: 1) Develop a basic UI for functionality | UI / Float: 1) Make UI look nice
High Level: 1) High Level Plan for 2 days 2) Logic Diagram Rev 01 | High Level: 1) Miro Board 2) Presentation
Not-Important / Urgent | Not-Important / Not-Urgent
Technical: 1) | Technical: 1)
UI / Float: 1) | UI / Float: 1)
High Level: 1) | High Level: 1)

## Timeline - Day 1
🗓 Day 1 – Kickoff & Prototype Foundations (Start 12:00)
Day | Time | Task | Description | Deliverable | Owner/Role | Dependencies | Completed
1 | 12:00–12:30 | Team Formation & Role Allocation | Assign key roles: Project Manager, Data Scientist, SME Liaison, Risk Analyst. Confirm deliverables and communication plan. | Agreed team roles & goal alignment | All | — | Yes
1 | 12:30–13:00 | Challenge Brief Review | Read and summarise the challenge statement, personas, dataset description, and success criteria. | Summary of objectives and evaluation metrics | High level | Kickoff | N/A
1 | 13:00–13:30 | Lunch Break | — | — | — | —
1 | 13:30–14:30 | Dataset Familiarisation | Review risk register data structure, columns, and examples. Identify inconsistencies or missing data. | Annotated data overview | Technical | Challenge brief
High Level
UI / Float
1 | 14:15–15:00 | Heuristic Review & Categorisation | Examine SME-provided heuristics; group them (e.g. clarity, mitigation strength, measurability). | Categorised heuristic table | SME Liaison | Dataset review
1 | 15:00–16:00 | Codify Heuristics | Translate heuristic statements into rule logic or natural language prompts for LLM or manual evaluation. | Table of codified heuristics | Risk Analyst + Data Scientist | Heuristic review
1 | 16:00–17:00 | Prototype Logic Setup | Create initial LLM prompt test or rule-based model using small sample of data. | Early prototype outputs | Data Scientist | Codified heuristics
1 | 17:00–17:30 | Pizza & Refreshments | Informal check-in and discussion of prototype insights. | — | All | —
1 | 17:30–18:00 | Day 1 Wrap-Up | Summarise progress, validate early findings with SME, and outline morning plan for full application. | EOD summary & next-step list | Project Manager | Prototype output

## Timeline - Day 2
🗓 Day 2 – Insight Generation, Feedback, and Final Submission
Day | Time | Task | Description | Deliverable | Owner/Role | Dependencies | Completed
2 | 08:30–09:15 | Registration & Refreshments | Arrive, set up, final check on data and environment. | Ready workspace | All | —
2 | 09:15–09:30 | Planning Huddle | Confirm Day 2 focus: apply heuristics at scale, produce insights, and build final presentation. | Updated task board | Project Manager | EOD1 summary
2 | 09:30–11:00 | Apply Heuristics to Full Dataset | Run codified heuristics against all risk data (manual, rule-based, or LLM-assisted). | Updated spreadsheet with heuristic scores/flags | Data Scientist | Codified heuristics
2 | 11:00–12:00 | Insight Generation | Analyse flagged risks and pattern trends (e.g. % vague, % weak mitigations). | Insight summary charts | Risk Analyst | Heuristic outputs
2 | 12:00–12:30 | SME Feedback Loop Design | Map how SME feedback could refine heuristic models (e.g. active learning, chatbot interface). | Feedback loop concept | SME Liaison | Insights summary
2 | 12:30–13:00 | Lunch Break | — | — | — | —
2 | 13:00–14:30 | Data Visualisation & Dashboard | Build clear, human-readable dashboard of risk quality results (traffic lights, scoring, charts). | Dashboard-ready Excel or slide visuals | Data Scientist | Insight summary
2 | 14:30–15:15 | Future Roadmap | Define potential system improvements and how heuristics could evolve over time. | Roadmap slide/table | Project Manager | Dashboard
2 | 15:15–16:00 | Final Presentation Build | Combine key outputs: problem, heuristics, insights, dashboard, feedback loop, and roadmap. | 5–7 slide presentation deck | All | Dashboard & roadmap
2 | 16:00–16:30 | Submission Prep & Upload | Quality check, save final files, and submit by deadline. | Final submission package | Project Manager | Presentation deck
2 | 16:30 | Submission Deadline | Deliver final outputs to judging team. | — | All | —
2 | 16:45 | Closing Talks | Attend closing remarks and judging feedback. | — | All | —
2 | 17:00 | Venue Closed | Pack down, backup files, and close out. | — | All | —

## Sheet2
Yes
N/A

## Deliverables
Deliverable | Description | Format / Notes | Deadline Tip
Presentation Video | A 5-minute recorded pitch + up to 2 minutes Q&A (judges’ questions arrive at midday). | MP4, 1080p, 16:9, clear audio, sponsor logos visible. Edit in Clipchamp. | Start recording by 14:00; upload early to avoid disqualification.
Presentation Slides | The visuals you use in your video (follow the provided Hack template). | PowerPoint or PDF with sponsor logos. | Submit same time as video.
Solution | The actual tool, spreadsheet, model, or script you built for the challenge. | e.g., Excel workbook, Python script, or prototype demo. | Ensure it opens and runs as described.
Supporting Materials | Any notes, documentation, or diagrams that help judges verify your claims. | Text file, README, or short PDF summary. | Optional but strongly recommended.