## Sheet1
Main Risk Cat. | Average Pre Factored Cost | Average Post Factored Cost | Average PreMit_Sched_Impact | Average PostMit_Sched_Impact
1. Business Strategy and Objectives | 4.00k | 2.15k | 128.7 | 77.17
2. Bid Management | 1.22k | 1.10k | 127.5 | 116.8
3. Competitors | No Data | No Data | No Data | No Data
4. Customers | 2.84k | 1.47k | 128.9 | 71.5
5. Project Management | 4.10k | 2.70k | 128.7 | 74.4
6. Contractual/Legal | 3.11k | 2.08k | 128.8 | 73.4
7. Finance | 3.41k | 3.28k | 128.3 | 72.3
8. System Engineering | 2.66k | 1.34k | 128.7 | 74.8
9. Hardware/Software development | 3.70k | 2.05k | 129 | 77.3
10. System Integration, Verification & Validation | 2.68k | 3.46k | 129 | 77
11. Supply chain | 2.87k | 1.89k | 128.7 | 78.5
12. Acquisition and offsets | 3.64k | 2.82k | 128.5 | 83.5
13. Logistic support and Services | 3.14k | 2.29k | 128.9 | 68.1
14. Other Risks and Contingencies | 3.52k | 2.14k | 128.8 | 91.1